## Dharun.R
Toll Pay
S.no | Name | Date | Time | Project Task | Status
1 | Dharun | 2017-12-08 | 10:30 - 05:00 | Tensor flow basic understanding and toolkits installation. | Completed
2 | Dharun | 2017-12-11 | 1:15 - 5:40 | MNIST in tensor flow | Completed
3 | Dharun | 2017-12-12 | 1:15 - 5:00 | softmax regressions | Completed
4 | Dharun | 2017-12-13 | 1:15 - 6:15 | working in matplot lib | Completed
5 | Dharun | 2017-12-14 | 1:15 - 6:15 | working in matplot lib | Completed
6 | Dharun | 2017-12-15 | 1:15 - 6:00 | object detection api | in progress
7 | Dharun | 2017-12-18 |  | Absent - add on classes
8 | Dharun | 2017-12-19 |  | Absent - add on classes
9 | Dharun | 2017-12-20 |  | Absent - add on classes
10 | Dharun | 2017-12-21 |  | Absent - add on classes
11 | Dharun | 2017-12-22 |  | Absent - add on classes
12 | Dharun | 2017-12-26 | 1:30 - 5:00 | database creation for user | Completed
13 | Dharun | 2017-12-27 | 10:00 - 7:00 | object detection api | in progress
14 | Dharun | 2017-12-28 | 1:15 - 6:30 | object detection api basic | Completed
15 | Dharun | 2017-12-29 |  | placement drive
16 | Dharun | 2017-12-30 |  | placement drive
17 | Dharun | 2018-02-01 | 1:15 - 7:00 | Custom Object Detection | in progress
18 | Dharun | 2018-03-01 | 1:30 - 5:00 | Object detection COCO dataset | Completed
19 | Dharun | 2018-04-01 | 9:30 - 6:00 | Object detection Open CV | Completed
20 | Dharun | 2018-05-01 | 1:15 - 4:30 | Tensorflow and open CV in Spyder | Completed
21 | Dharun | 2018-06-01 | 1:30 - 6:00 | Custom Image labeling | Completed
22 | Dharun | 2018-08-01 | 1:15 - 7:00 | Object training phase (num plate in car) | in progress
23 | Dharun | 2018-09-01 | 1:15 - 7:00 | Object training phase (num plate in car) | in progress
24 | Dharun | 2018-10-01 | 1:15 - 7:00 | Object training phase (num plate in car) | in progress
25 | Dharun | 2018-11-01 | 1:30 - 6:00 | testing phase | in progress
26 | Dharun | 01-16-2018 | 9:30 - 6:00 | testing phase | in progress
27 | Dharun | 01-17-2019 | 1:15 - 7:00 | testing phase | in progress
28 | Dharun | 01-18-2019 | 1:15 - 7:00 | testing phase | in progress

## Andrine.V.T.
Toll Pay
S.no | Name | Date | Time | Project Task | Status
1 | Andrine | 2017-12-08 | 10:30 - 05:00 | Tensor flow basic understanding and toolkits installation. | Completed
2 | Andrine | 2017-12-11 | 1:15 - 5:40 | Python basics | Completed
3 | Andrine | 2017-12-12 | 1:15 - 5:00 | Python programming | 20%
4 | Andrine | 2017-12-13 | 1:15 - 6:15 | Python Programming | 70%
5 | Andrine | 2017-12-14 | 1:15 - 6:15 | module planning | Completed
6 | Andrine | 2017-12-15 | 1:15 - 6:00 | UI developing login | Completed
7 | Andrine | 2017-12-18 |  | Absent - add on classes
8 | Andrine | 2017-12-19 |  | Absent - add on classes
9 | Andrine | 2017-12-20 |  | Absent - add on classes
10 | Andrine | 2017-12-21 |  | Absent - add on classes
11 | Andrine | 2017-12-22 |  | Absent - add on classes
12 | Andrine | 2017-12-26 | 1:30 - 5:00 | database creation for user | Completed
13 | Andrine | 2017-12-27 | 10:00 - 7:00 | toll details database | 70%
14 | Andrine | 2017-12-28 | 9:00 - 6:30 | dynamic user login pages | 70%
15 | Andrine | 2017-12-29 |  | Placement drive
16 | Andrine | 2017-12-30 | 1:15 - 4:30 | database creation for trasation | Completed
17 | Andrine | 2018-02-01 | 1:15 - 7:00 | UI developing login | in progress
18 | Andrine | 2018-03-01 | 1:30 - 5:00 | php session creation | Completed
19 | Andrine | 2018-04-01 | 9:30 - 6:00 | dynamic dashboard | Completed
20 | Andrine | 2018-05-01 | 1:15 - 8:00 | login validation | Completed
21 | Andrine | 2018-06-01 | 1:30 - 6:00 | fields checking login | Completed
22 | Andrine | 2018-08-01 | 1:15 - 7:00 | registartion processing | Completed
23 | Andrine | 2018-09-01 | 1:15 - 7:00 | UI dashboard | in progress
24 | Andrine | 2018-10-01 | 1:15 - 7:00 | UI dashboard | in progress
25 | Andrine | 2018-11-01 | 1:30 - 6:00 | php embedding over admin dashboard | Completed
26 | Andrine | 01-16-2018 | 9:30 - 6:00 | camera connection with the site | Completed
27 | Andrine | 01-17-2019 | 1:15 - 7:00 | map connectivity | in progress
28 | Andrine | 01-18-2019 | 1:15 - 7:00 | php embedding over user dashboard | in progress